## grant submission
| Steps in our Grant notification/Processing System | Rationale for notication and steps taken by the Research Office
1 | PI decides to submit a grant, request access to RedCap database to submit a PIF (Project Information Form) | Assumption is that the person notified the department chair of their intentions (PI is reminded on the PIF to notifiy their department chair of their plans). Further, the PI verifies this by checking the box on the PIF.
2 | PI completes the Project Information Form located on Research Office RedCap Database. RedCap generates email alerts to the follow individuals
| Department Chair and ADR designees | The deadline for the grant proposal gets on the RO calendar
| College of Nursing Finance Department | Finance gets budget review on their calendar
| The faculty member who submitted | Faculty member get verification that the ticket was received
| RO Adminstrative Staff | Schedule Initial consultation meeting
3 | Prep for the Initial Meeting between RO and the PI
| ADR designee or adminstrative staff | Place it as a discussion item at the weekly RO meetings
| Adminstrative staff | Prepare a grant submission check list specific for the grant
| ADR and ADR Designee | Review the call for the grant
4 | At the meeting the RO and use the grant submission worksheet to obtain key information for planning the submission.
| List of research team (verify that Dept chairs were informed) | Get a list of CON/non CON personel. If they have not done so, direct them to the notification portal
| Budget/admin contacts (including ORA equivalent from other Campus) | ORA will need this information, helps to have list of people in case the signoffs get snagged.
| Query whether they talked to the funder program officer. | If new researcher, they may not know to do this.
| Likely list of Biosketchs, Letters of Support | Needed if they want us to collect them for them. Otherwise, we don't use that part of the worksheet.
| Verification of RCR and COI training | New ORA policy--PI must attest to adherance to these policy for not just them but all key personnel
| Assistance with Other Support documentation (by October 1st) | Created a worksheet that will help investigators to create the other support table for each funded or pending grant. Once they do it once, it should be able to add to it and share with the Department Chair.
| Desire for a mock review or Consultant to review drafts | Set plan for a writing schedule, assist in locating reviewer, and arranging with Finance to set up an independent contractor agreement.
| Review checklist (contents of the grant) per RFA instructions. | PI is offered a copy of the grant checklist. RO staff uses this at weekly meeting to assess progress with the submission.
| RO updates sooner track with information about coinvestigators, primary institution, submission due dates. | preping system for sending out reminders.
(Automated reminders to PI and Support staff should be biweekly follow-up until the Intent changes status to filed/withdrawn)
5 | After the Initial consultation meeting, PI sends and email listing the agreed upon deadlines for document to arrive at the research office. This varies but all grants going through CON for review must have at least:
| NIH budget form with complete list of coinvestigators and Consultants | Allows department chair one last notification of facutly percent time on the grant, Finance to have materials to check accuracy of spreadsheet and match to justificaion, and ADR to verify materials in SoonerTrack is the same as budget materials submitted.
Budget Justficiaton, Specific Aims, and Approach Section
The ADR will help anyone with the creation of the study budget--must have a clear, detailed writup of the approach section/methods. The RO have templates and tips on budgeting and biosketches. The ADR can also provide assistance in aligning aims with approach/methods/analysis/budget/justificiation (must have at least 3 business days notice)
Junior Professors will be offered consultation/assistance in creating (pending adequate admin support)
Biosketches
Facilities and other Resources, Equipment, Protection of Human subject, Resource Sharing Plan
Study Timelines
Letters of Support
Subcontract Materials
Other Support Materials
Forms requiring signature authority from Dean or ORA or other
Subcontracts should be started as soon as it is clear that they are needed. After the initials meeting, the PI should keep the RO informed in any additional investigators, consultants, or services that are coming from outside OUHSC (including Norman and Tulsa). These documents can take 1-2 weeks for complete. So, the sooner the better.
6 | RecCap will generate a email to the SPA/research Adminstrator/ADR designate no later than 2 week before due for ORA review.
| Email SPA at ORA that a SoonerTrack is Coming with specific Date 2 | Since the SPA does not see the ticket until submitted. It gives them a heads up of the volume of work.
| Email SPA any forms that ORA will need to fill out for PI. | Subcontracts and independent contract agreement require approvals between ORA and GCA. Can take up to 2-3 days to resolve.
7 | 1-3 days before submitting to ORA/1 week before the grant is due to funder. The last set of reminders, going to
| Department Chair and ADR | so they are available to review materials and sign off in Soonertrack grants
| designee at Nursing Finance | so they ar available to review budget/justificaoin by a certain date.
| PI | remind them of the due dates for materials to go to their department chair and finance.
| In the meantime, the PI should begin (if not started) preparing the funders document upload site | RO is available to advise (including providing template pages)
Due date for ORA 3 Day Review Policy: All proposals in final form submitted to ORA 3 full University business days prior to sponsor deadline. Example: If a proposal is due Friday at 5 PM, submission to ORA (not leaving the College of Nursing or waiting for coinvestigator approval from another department) no later than 5 PM Tuesday (includes routed SoonerTrackticket) If you miss this deadline, email waiver from Vice President for Research (Dr. Ogilvie) required
8 | PI send body of the grant, NIH spreadsheet/OU budget justificaton, funder budget materials to Department Chair, ADR, and Finance.
| Finance reviews, sends emails to PI with any concerns. PI returns budget to Finance until a correct copy is generated | One last notification to Department Chair of the % effort request allows RO to know deposition of budget.
| PI can request assistance with revisions to the budget spreadsheet and justification--send an email requesting help | RO staff and ADR will provide assistance as requested.
ADR will read this draft to make sure budget fits with approach section.
10 | PI sends all grant documents to the research office. Contents of this packet depends on grant mechanism but will always include:
| RFA or submission instructions, NIH budget page, and budget justification, Other support pages | mostly the parts that ORA are interested in.
| Grant proposal (can often get away with not having the biosketches, facilities, capital equipment, letters of support ect). | Get started on this early, plan at least a weekend to upload and check the formating/grammar/spelling of the documents)
11 | PI must upload all document to the the funder portal. Key pages (especially cover page with orgnaizational information must be in before posting to soonertrack. They should be there at least the day before the grant is submitted.
12 | RO staff set up the SoonerTrack Ticket and uploads files to SoonerTrack.
| Number the files in the order that they will be uploaded, saves copy on the CON Research Restricted Folder | easier to upload in soonertrack (make sure you got what you need before submission). Order reflect items listed on the RO project worksheet)
| Email ADR that the SoonerTrack packet is ready for review. | Last check before launched. ADR verifies correct entries into soonertrack.
| ADR releases Ticket for PI/PD review. Emails PI to look for soonertrack email. | Last check of error for setup of Soonertrack by Designee and anything missing in application.
13 | Soonertrack is released for PI participation and PI department approvals
| SoonerTrack sends two email to the PI | The first is for a final review of the packet uploaded by RO staff The second is to complete COI and Regulatory Items, entering of the department chair, and college dean, and to verify participation on the grant.
| College of nursing PI and CoIs completes COI, NIH regulatory, and verify participation on the grant | This step will go on until all investigators provide COI/verify participation
| Department Chairs receive emails for each faculty investigator on the grant, prompted to review and approve | This step has to happen for each faculty member within the CON--must be done before the ADR can approve
| Once all faculty department chairs has approved participation, the ADR goes in and grants the Dean's approval. | Still having problems getting SoonerTrack to allow me to sign--I've been doing it because I can edit the document.
14 | RO monitors SoonerTrack ticket progress to the other Colleges.
| RO Instruct the PI to email each CoI, instructing them to approve their participation and to be sure to list the person who signs off their time for their college on the form | Following the SoonerTrack emails, the RO designee monitors the verification of faculty outside the CON
Office administrator to checks first thing in the morning (or sooner and at least q2hr) for remaining signoffs.
14 | (Soonertrack Internal Review) When Soonertrack moves from Faculty to Internal Review
| Email ORA (SPA and SPO) to let them know that the grant (give the GRF number) is ready for their review or is missing some component and remind them of anything they should have already got for the submission. | ORA will usually answer back at least 2 days before the grant is due to funder.
PI needs to be available to make modifications.
15 | ORA approves (after revisions) and institutional signature provided and ready to submit.
ORA notifies PI (copies RO) to get final okay to submit document
PI should respond to ORA when ready, copy RO
16 | Post submission review
| RedCap generates remiders to PI, RO, ADR | quality control, fidelity of post submission review
| PI sends a PDF (or word document if the proposal is submitted in website windows) to the research office. | archiving
| Document upload to research restricted folder | archiving
| Document forwarded to finance | archiving
| ADR and PI reads the submitted document (day after submitted) | RO will review to see if there are any obvious errors (typically give 72 hours to correct)
17 | Final login of grant information in RED Cap
| RO office completes the remainder of RedCap information | this information includes amounts, dates of review, council, expected start date, funds requested.
| RedCap will send email to PI inquiring status of grant- | this will be done the last week of the month the grant was reviewed.